## GUIDELINES
BRD + ESTIMATION TEMPLATE — GUIDELINES
• This template combines business requirements documentation (BRD) and effort estimation into a single working file.
• Start with the "User Stories" sheet — enter epics, features, user stories, and acceptance criteria.
• Use the "Epic" (col B) and "Feature / Touchpoint" (col C) dropdowns/filters to navigate or filter stories.
• Assign a t-shirt size for each track (Design, FE, BE, AI/Data) using the dropdowns in columns I, K, M, O.
• Man-days auto-calculate from each track's sizing table (sheets 8–11).
• View aggregated effort in the "ESTIMATION SUMMARY" sheet — counts and man-days update automatically.
• Adjust the Optimistic (−10%) and Pessimistic (+20%) factors on the Estimation Summary to model ranges.
• Use the "Complexity Guide" sheets (12–15) to decide which t-shirt size to assign before entering estimates.
• Blank templates: Notification Mapping, RBAC, Data Fields, and LOV — fill these in as requirements are defined.
• Never edit the T-Shirt Sizing tables (sheets 8–11) unless the team agrees to change the man-day rates.

## ESTIMATION SUMMARY
ESTIMATION SUMMARY
|  | UX DESIGN |  |  | FRONTEND (FE) |  |  | BACKEND (BE) |  |  | AI / DATA
| SIZE BUCKET | NO. | SIZE | MD | NO. | SIZE | MD | NO. | SIZE | MD | NO. | SIZE | MD
| 2XL |  | 2XL |  |  | 2XL |  |  | 2XL |  |  | 2XL
| XL |  | XL |  |  | XL |  |  | XL |  |  | XL
| L |  | L |  |  | L |  |  | L |  |  | L
| M |  | M |  |  | M |  |  | M |  |  | M
| S |  | S |  |  | S |  |  | S |  |  | S
| XS |  | XS |  |  | XS |  |  | XS |  |  | XS
TOTAL
| MAN DAY ADJUSTMENT FACTOR | 1 | (Change this value to apply a team efficiency multiplier, default = 1)
| EFFORT RANGE | Design MD |  |  | FE MD |  |  | BE MD |  |  | AI MD |  |  | ADJUSTMENT %
| Optimistic | [12 empty] | 10%
Most Likely
| Pessimistic | [12 empty] | 20%
TOTAL OVERALL EFFORT ESTIMATION
| Scenario | Most Likely
| Track | Approx. Man-Days
UX Design
Frontend (FE)
Backend (BE)
AI / Data
TOTAL

## User Stories
USER STORIES
USER STORY DETAILS | [7 empty] | UX DESIGN |  | FRONTEND (FE) |  | BACKEND (BE) |  | AI / DATA |  | ASSUMPTIONS & ASSESSMENTS
ID | EPIC | FEATURE / TOUCHPOINT | STORY ID | USER STORY | ACCEPTANCE CRITERIA | PRIORITY | RELEASE | SIZE | MD | SIZE | MD | SIZE | MD | SIZE | MD | UX DESIGN ASSUMPTIONS | FE / TECH ASSUMPTIONS | BE / API ASSUMPTIONS | AI / DATA ASSUMPTIONS | INTEGRATION ASSESSMENT | DEPENDENCIES
↓ Copy row 103 downward to add more stories

## Notification Mapping
NOTIFICATION MAPPING
S/No. | User Story ID | Notification Trigger & Description | Triggered By | Recipient(s) | In-App | Email | SMS | Push | Remarks

## RBAC
ROLE-BASED ACCESS CONTROL (RBAC)
Legend: ✓ = Access permitted ¦ ✗ = No access ¦ − = Not applicable ¦ C = Conditional access
S/N | Epic / Feature Group | Feature | Role 1 | Role 2 | Role 3 | Role 4 | Role 5

## Data Fields
DATA FIELDS
S/N | Module / Screen | Field Name | Field Label (Display) | Data Type | Mandatory | Editable | Visible To Roles | Validation Rules | LOV Reference | Remarks

## LOV
LIST OF VALUES (LOV)
A List of Values (LOV) groups reference/dropdown options by list name. Each row defines one value within a list.
S/N | List Name | Value (Display) | Code (System) | Description / Meaning | Active | Remarks

## Design(T-Shirt Sizing)
DESIGN EFFORT T-SHIRT SIZING
N.A. | 0
XS | 1
S | 2
M | 3
L | 5
XL | 10 | << Consider decomposing
2XL | 20 | << Needs further decomposition
Usage Notes:
Refer to the Complexity Guide before assigning sizes. XL and 2XL items should be broken down before sprint planning.
N.A. = task not applicable to this track for the given user story.

## FE(T-Shirt Sizing)
FE EFFORT T-SHIRT SIZING
N.A. | 0
XS | 3.5
S | 6
M | 12.5
L | 20
XL | 32.5 | << Consider decomposing
2XL | 65 | << Needs further decomposition
Usage Notes:
Refer to the Complexity Guide before assigning sizes. XL and 2XL items should be broken down before sprint planning.
N.A. = task not applicable to this track for the given user story.

## BE(T-Shirt Sizing)
BE EFFORT T-SHIRT SIZING
N.A. | 0
XS | 3.5
S | 6
M | 12.5
L | 20
XL | 32.5 | << Consider decomposing
2XL | 65 | << Needs further decomposition
Usage Notes:
Refer to the Complexity Guide before assigning sizes. XL and 2XL items should be broken down before sprint planning.
N.A. = task not applicable to this track for the given user story.

## AI(T-Shirt Sizing)
AI EFFORT T-SHIRT SIZING
N.A. | 0
XS | 2
S | 5
M | 10
L | 20
XL | 40 | << Consider decomposing
2XL | 80 | << Needs further decomposition
Usage Notes:
Refer to the Complexity Guide before assigning sizes. XL and 2XL items should be broken down before sprint planning.
N.A. = task not applicable to this track for the given user story.

## Design(Complexity Guide)
DESIGN COMPLEXITY GUIDE
| DIMENSION | SMALL (XS–S) | MEDIUM (M–L) | LARGE (XL–2XL)
| Process Steps | ≤3 sequential actions | 4–9 process steps across the workflow | 9+ process steps
| Data Variations | ≤3 distinct states or sets | 4–8 distinct states or sets | 9+ distinct states or sets
| Logics | No conditional branching or nested conditions | Single level of conditional branching; excludes deeply nested or multi-layered conditions | Multiple levels of conditional branching and nested conditions
| Visual Asset | Basic graphics or stock imagery with minimal customisation | Custom or adapted graphics up to 4 assets; individual asset sizes ≤500×500px | Custom or adapted graphics — 5+ assets, or individual asset sizes >500×500px
If any single dimension reaches the threshold for a given size, that size applies — use the highest triggered threshold across all 4 criteria.

## FE(Complexity Guide)
FE COMPLEXITY GUIDE
| DIMENSION | SMALL (XS–S) | MEDIUM (M–L) | LARGE (XL–2XL)
| UI fields / components | ≤5 fields, minimal scrolling | ≤12 fields, 50% need validation | >12 fields, heavy scrolling
| UI events | ≤2 UI events | ≤5 UI events | >5 UI events
| Content | Static content | Mostly static; images, rich text | Dynamic content; images/videos/feeds
| Data transformation | None | Minimal transformations | Heavy data/content transformations
| Transactions | None | None | Page involves transactions
| Integration points | None | <3 integration points | ≥3 integration points
| Security | No security requirements | No security requirements | Security requirement applies

## BE(Complexity Guide)
BE COMPLEXITY GUIDE
| DIMENSION | SMALL (XS–S) | MEDIUM (M–L) | LARGE (XL–2XL)
| DB / service integrations | None | ≤3 integrations | >3 integrations
| Routing | Simple | Simple | Complex content-based routing
| Validation | Message structure level | Message structure level | Field-level validation
| Aggregation | No | No | Yes
| Transformation | Straight mapping | Mapping and translation | Complex mapping, conditional, cross-parser
| Processing logic | Simple pass-through | Simple multi-level, some control logic | Complex control logic, multiple business rules

## AI(Complexity Guide)
AI COMPLEXITY GUIDE
| DIMENSION | SMALL (XS–S) | MEDIUM (M–L) | LARGE (XL–2XL)
| Data volume | Single table, <10K rows, batch ingest | Multiple tables or streams, up to 1M rows | Real-time streams, 1M+ rows, multi-source joins
| Model complexity | Rule-based logic or single pre-trained model | Fine-tuned model or ensemble, defined features | Custom model training, RAG pipeline, or multi-agent
| Evaluation / iteration | Single benchmark, no retraining | 2–3 evaluation cycles, hyperparameter tuning | Continuous retraining loop or A/B testing
| Infrastructure | Existing compute, no MLOps setup needed | Requires pipeline orchestration (e.g. Airflow) | Full MLOps: model registry, monitoring, drift detection
| Data quality work | Clean, structured input | Moderate cleaning, schema mapping | Heavy normalisation, deduplication, or label work
| Integration points | Standalone script or notebook | REST API or database integration | Multi-system integration, real-time serving